# Logicopilot AI — 2-Month Panel Implementation Plan

Total Duration: 42 Working Days (8 Weeks)

This plan focuses entirely on the product panels and features. (Technical setups like servers and databases are built in parallel and baked into these times).

Format: Left = Feature | Centre = Max Duration | Right = Assignee (fill in yourself)

### 1️⃣ Security & Access Module (2 Days)

| Feature | Duration | Assignee |
| --- | --- | --- |
| Secure Login System — Login pages for Super Admins, Tenant Admins, and Operators. | 1 days |  |
| Role-Based Access Control — Locking down screens so users can only see what their role allows. | Half day |  |
| Multi-Company Data Isolation — The core logic ensuring that no company can ever see another company's documents or data. | Half days |  |

### 2️⃣ Super Admin Panel & Onboarding Wizard (7.5 Days)

The portal where admins configure new customers and train templates visually.

| Feature | Duration | Assignee |
| --- | --- | --- |
| Customer/Tenant Creation — UI to register a new company (e.g. 4S Logistics) and set their region/currency. | Half day |  |
| Custom Label Builder — Interface to create data tags (e.g. `invoice_no`), define data types, and toggle "Verify with other document". | 1 days |  |
| Template Reference Uploader — Tool to upload sample PDFs (BL, Invoice) and render multi-page visual previews. | 1 days |  |
| Interactive Bounding Box Cropper — The drawing canvas where admins highlight fields using the 5-color system (Red, Green, Blue, Yellow, Purple). | 1.5 days |  |
| Cross-Document Verification Linker — Left sidebar UI that lets admins link a label from Document A to a target area on Document B. | 1 days |  |
| AI Transformation Prompt Editor — Input field to write natural language rules for how extracted data should be formatted. | 1 day |  |
| AI Prompt Training Loop & Correction UI — The testing screen where admins can correct AI mistakes, which automatically updates the system's training rules. | 1.5 days |  |

### 3️⃣ Tenant Admin Panel (4 Days)

The portal where a specific customer manages their own team and settings.

| Feature | Duration | Assignee |
| --- | --- | --- |
| Operator Account Management — UI to invite, create, edit, and disable daily operator user accounts. | 1 day |  |
| Tenant Formatting Settings — Configuration page to enforce standard date structures and currency symbols across the tenant. | 1 day |  |
| Field Hint & Description Editor — Tool to add helper text to document fields so operators know what to look for. | 2 day |  |

### 4️⃣ Daily Operator Dashboard (7 Days)

The day-to-day workspace where operations teams process files and handle exceptions.

| Feature | Duration | Assignee |
| --- | --- | --- |
| Multi-file Transaction Uploader — Tool to group multiple files (BL + Invoice + Packing List) into one "transaction". | 1.5 days |  |
| Side-by-Side Extraction Results Viewer — Split screen showing the document PDF on the left and the editable extracted AI fields on the right. | 2 days |  |
| Discrepancy Alert & Verification Panel — Alert cards that flag mismatches (e.g., weights differ between docs) requiring operator approval. | 1.5 days |  |
| Manual Correction & Auto-Training Trigger — System that lets operators fix typos and automatically sends that feedback to train the AI. | 1 day |  |
| Transaction History & Status Viewer — Table showing all past transactions, their success/error states, and data export buttons. | 1 day |  |

### 5️⃣ AI Document Extraction Engine (9 Days)

The hidden brain of the system that reads documents, understands context, and checks the math.

| Feature | Duration | Assignee |
| --- | --- | --- |
| Document Text Scanner — Connecting to Google Cloud Document AI to scan images and return raw digital text. | 2 days |  |
| Semantic Anchor Auto-Detection — Logic that automatically identifies labels near a cropped box (like the word "Invoice No:") to build smart search prompts. | 2 days |  |
| OpenAI Extraction & Transformation Pipeline — The core engine that sends OCR text + admin prompts to OpenAI to extract perfectly structured data. | 3 days |  |
| Cross-Document Semantic Verification Agent — The AI agent that cross-checks meaning across documents (e.g., knowing 1.5 MT = 1500 KGS). | 2 days |  |

### 6️⃣ RPA Web Recorder & Headless Playback (6.5 Days)

The visual automation tool for recording web entries and the background runner that executes them.

| Feature | Duration | Assignee |
| --- | --- | --- |
| Embedded Live Browser View — The window inside the software that loads the target website (ERP/Customs portal) for the admin to see. | 2 days |  |
| Drag-and-Drop Form Input Mapper — UI allowing admins to drag document labels (like `invoice_no`) and drop them directly onto website text boxes. | 1.5 days |  |
| User Action Recorder — Background tracker that records all mouse clicks, typing, and waits, while generating unbreakable rules to remember actions. | 1.5 days |  |
| Invisible Background Playback Engine — The invisible backend robot that opens the browser on the server, logs in, and types the data automatically. | 1.5 days |  |

### 7️⃣ Quality Assurance & Testing (6 Days)

Comprehensive testing phase to ensure all panels and AI components work flawlessly before launch.

| Feature | Duration | Assignee |
| --- | --- | --- |
| Testing: Security & Access Module — Verifying logins, testing role restrictions, and ensuring strict data isolation between companies. | 1 day |  |
| Testing: Super Admin Panel — Testing label creation, PDF uploads, bounding box drawing accuracy, and cross-document linking workflows. | 1 day |  |
| Testing: Tenant Admin Panel — Verifying operator account creation, disabling accounts, and checking formatting rules. | 1 day |  |
| Testing: Daily Operator Dashboard — Uploading large file batches, verifying the split-screen viewer, and testing the manual correction feedback loop. | 1 day |  |
| Testing: AI Extraction Engine — Feeding blurry or complex documents to test OCR accuracy, and verifying the AI's cross-document math/logic checks. | 1 day |  |
| Testing: RPA Web Recorder & Playback — Recording complex website interactions and testing the background bot to ensure it types data perfectly without crashing. | 1 day |  |

Total Estimated Build Time: 42 Working Days (2 Months) + Testing Phase